Operations Advisory Committee Meeting

Community Manager’s Report for Month of October 2013

Respectfully Submitted by Steve Dean

I.      Community Manager Budget

74.05% funding used with 83.3% time elapsed.

II.	Water Distribution System:

- Install pitless adapter, pump and motor  11/5/13 – 11/7/13 (complete)

- Install underground piping  11/8/13 – 11/15/13

- Pour concrete footers and slab for pump house  11/8/13 – 11/15/13

- Install pump house and interior piping  11/18/13 – 11/29/13

- Electrical work  11/25/13 – 12/6/13

- Install Detention tank  12/2/13 – 12/6/13

- Install Generator and propane tank 12/2/13 – 12/6/13

- Install CL2 system and HACH  Analyzer  12/2/13 – 12/6/13

- Startup and demobilization  12/9/13 – 12/13/13

- Install security fence

- Underestimated SMECO cost to run power to Well #5 by $3,800.

- Repaired underground water leak on Aspen Rd.

- Water tower exterior re-painted.

- Wells 1 & 4 operating normally.

III.	Buildings, Grounds, Roads and Pool

- Cut bamboo behind shop.

- Reviewed numerous vegetation removal permits.

- Cleared lot and removed stumps on corner lot at Birch Rd. and Bluebell Rd. for P&G.

- Removed bamboo in RV area.

- Re-keyed all remaining padlocks.

- County requiring SCA to contract surveyor or engineer licensed in the State of Maryland to have drainage computations prepared for each storm water drainage system.

- Installed newspaper recycling bins in Gate A dumpster area.

Pool

- Met with Billy Gray and Tay Vaughan to discuss pool upgrades.

Community House

- Re-keyed all locks.  Setup for Halloween party and hayride.

- Completed the Red Cross First Aid/CPR/ AED Training.  Entire SCA Staff is now certified.

Chestnut Cabin

- Spread mulch on hill between CC and Bluebell Rd.

- Re-keyed all locks.

IV.	Beaches and Ravines

- Moved several abandoned boats from South Beach to boat yard area for disposal.

- Worked on toe revetments.  Installed approximately 50 tons of surge rock.  Need to install two more 12’ basket to complete first section.

- Made repairs on steps and walkways in ravines.